# CDMS 2.0 to 3.0 Migration Process – Detailed Plan

This document outlines the full process and enhancements for migrating from CDMS 2.0 to CDMS 3.0, including planning, execution, validation, and governance practices.

# CDMS Migration Process Plan

Project: CDMS 2.0 to CDMS 3.0 Migration

Target Completion Date: Within 4 weeks

Migration Lead: DBA Team & CDMS Development Team

## 1. Assess Source and Target PostgreSQL Databases

Target max time : 1-3 days

- Document all tables, sequences, indexes, and functions in CDMS 2.0

- Analyze object sizes and total database size

- Verify target CDMS 3.0 DB structure and capacity planning.

- 1. pre enviornment setup

| SL# | Pre-requisite Item | Type | Memory | Core | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Server 2 nos. | WINDWOS (2) | 64 GB for windows, 32 GB for LINUX | 16 Core CPU | Firewall Port Access Between Two Servers for Internet Connectivity |
| 2 | Postgresql interection tools | Pgadmin | NA | NA |  |

- database link establish and testing purpose

## 2. Database Object Mapping

Target max time :  3-5 day

- Prepare full table and column mapping sheet (CDMS 2.0 → CDMS 3.0)

- Highlight renamed or dropped/added columns

- Review changes in schema structure and normalization

## 3. Scripting Phase

Target max time :  5–7 day

- Finalize migration scripts for objects like table, indexes, and constraints

- find object where ETL support required on migration.

## 4. Data Migration Execution (dry Run)

Target max time :8-9 day

- script execution a

- recording execution and completion time

## 5. Enforce Constraints Post Migration

Target max time :8-9 day

- Apply primary and foreign key constraints and check constraint and default values  load.

## 6. Reset Database Sequences

Target max time : 8-9 day

- scripts for the production database sequence capture.

- Reset sequence migration database as per production.

## 7. Post-Migration object validation  (Production Plan)

Target max time : 10-2day

- object count match Finalize source and target schema — no further changes allowed

- object data count matching.

## Requried  environment for Migration Execution Plan

| SL# | Pre-requisite Item | Type | Memory | Core | remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | VM 1nos. | WINDWOS (1) , L | 3 GB for windows, | 14 Core CPU | Server team |
| 2 | Postgresql interective tool | pgadmin | NA | NA | CSM (Tool should be downloaded in Pre Prod environment) |
| 3 | - Script editor | Notepad ++ | NA | NA | CSM ( Download from Oracle site) |

## 10. migration object list and summary

| SL # | Database Schema name | Total Table | Require Table |
| --- | --- | --- | --- |
| 1 | Total no of objects | 200 | 66 |
| 2 | Master tables list | 42 | 38 |
| 3 | Transection tables list | 159 | 28 |
| 4 | New tables (cdms3.0 master+transection) | 40 | 40 |

## Migration Activity and Timeline

| PRODUCTION ENVIRONMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| SL # | Activity Name | Start Date | End Date | remarks |
| 1 | Source database (postgres) study and analysis |  |  | Completed |
| 2 | PostgreSQL Schema wise object identification |  |  | Completed |
| 3 | PostgreSQL database object's script generation | 8-Aug-25 | 14-Aug-25 | CSM DB TEAM |
| 4 | PostgreSQL capture object's script execution on Postgresql new Prod database | 18-Aug-25 | 18-Aug-25 | CSM DB TEAM |
| 5 | Structure data type testing and validation | 19-Aug-25 | 19-Aug-25 | CSM DB TEAM |
| 6 | Referential integrity script execution | 20-Aug-25 | 20-Aug-25 | CSM DB TEAM |
| 7 | Data migration | 21-Aug-25 | 22-Aug-25 | CSM DB TEAM |
| 8 | Tables sequence updation | 23-Aug-25 | 23-Aug-25 | CSM DB TEAM |
| 9 | Testing | 24-Aug-25 | 25-Aug-25 | CSM DB TEAM |

- Migration ETL Proposal, including:

- Data extraction from CDMS 2.0 (schema based backup using pg_dump)

- Data transformation logic( data type mapping, date/time format handling, null values, etc.)

- Data loading strategy into CDMS 3.0 (using tools like pgadmin, dbeaver, psql, 	pg_restore)

- Error handling and logging mechanism( any d)

- Batch-wise load plans (e.g., based on primary key ranges or timestamps)

Risk  & Rollback Plan

For safety and integrity of data throughout the migration we will take the backup and rollback if any issue.

## Backup

- Database Backup: Before starting the migration process, will take full backup of postgresql database.

- Application Backup: We will ensure a copy of application code, scripts, and configuration files related to postgresql new version of  database.

## Rollback

Below steps would be taken for rollback.

- Activate postgresql database

- Update application configuration and revert to previous state

Test rollback and check data consistency

## Risks

Below would be some risks in the project while migrating from cdms2.0 to postgresql in cdms project.

- There is a risk of data loss during migration due to errors in data extraction, transformation, or loading processes. Ensuring data integrity throughout the migration

- Applications that were designed to work with cdms2.0 may need significant modifications to function correctly with cdms3.0, potentially causing compatibility issues.

- Like collection data which is come to applicaiton so after migration data may be mismatch.