## CDMS Migration Process – CDMS project

As part of the CDMS project migration, the following steps will be followed in coordination with the DBA and development teams:

- Assess Source and Target PostgreSQL Databases

  - Review and document the total number of objects (tables, sequences, indexes, functions) in the source database

  - Check the database size and individual object sizes for performance considerations

  - Perform a similar assessment for the target database to ensure compatibility and capacity

- Database Object Mapping

  - Create a detailed table and column mapping document between CDMS 2.0 (source) and CDMS 3.0 (target)

  - Identify renamed tables/columns and new schema structures

- Scripting Phase

  - Prepare DDL scripts for object creation (tables, indexes, constraints) in the target environment

  - Develop ETL scripts or transformations for value mappings where needed

Manual Script object to object data migration

- Data Migration Execution

  - Perform structured data migration using validated scripts

  - Migrate data in batches if needed for large volume tables

- Enforce Constraints

  - Enable and validate primary key and foreign key constraints after data loading

  - Ensure data integrity and referential rules are respected in the new schema

- Reset Database Sequences

  - Identify and reset auto-increment sequences to align with the latest migrated records

  - Confirm sequence values do not cause conflicts in inserts

- Pre-Migration Validation & Finalization

  - Begin only after finalizing the source and target schemas

  - Freeze changes on the source system to prevent drift during migration

- Dry Run & Timing Plan

  - Execute a dry run of the full migration process in a staging environment

  - Record timings and issues, and finalize the official migration plan and execution schedule

  - Random data validation

Note:
Please refer to the supporting document containing a sample migration strategy for detailed guidance on each step of the database migration process.

## 📦 CDMS Migration Process Plan

Project: CDMS 2.0 to CDMS 3.0 Migration
Target Completion Date: Within 4 weeks
Migration Lead: DBA Team & CDMS Development Team

### ✅ 1. Assess Source and Target PostgreSQL Databases

🗓 Target Deadline: Day 1–3

- Document all tables, sequences, indexes, and functions in CDMS 2.0

- Analyze object sizes and total database size

- Verify target CDMS 3.0 DB structure and capacity (storage, parameters)

### ✅ 2. Database Object Mapping

🗓 Target Deadline: Day 3–5

- Prepare full table and column mapping sheet (CDMS 2.0 → CDMS 3.0)

- Highlight renamed or dropped/added columns

- Review changes in schema structure and normalization

### ✅ 3. Scripting Phase

🗓 Target Deadline: Day 5–7

- Finalize DDL scripts for tables, indexes, and constraints (already available)

- Prepare transformation logic or ETL scripts where needed

- Prepare manual data copy scripts (object to object)

### ✅ 4. Data Migration Execution (Test Run)

🗓 Target Deadline: Day 8–10

- Load sample/dummy data into target

- Perform initial data migration for small tables

- Batch load larger tables (e.g., in 10K/50K rows per batch)

- Record performance stats and tuning metrics

### ✅ 5. Enforce Constraints Post Migration

🗓 Target Deadline: Day 11–12

- Apply primary and foreign key constraints post data load

- Validate referential integrity using checks or custom scripts

### ✅ 6. Reset Database Sequences

🗓 Target Deadline: Day 12–13

- Identify all serial, bigserial, or nextval()-based columns

- Reset sequence values using setval() based on max ID in each table

- Insert dummy rows to test auto-increment behavior

### ✅ 7. Pre-Migration Finalization (Production Plan)

🗓 Target Deadline: Day 14–15

- Finalize source and target schemas — no further changes allowed

- Freeze writes in source system (optional: read-only mode or maintenance window)

- Communicate freeze schedule with stakeholders

### ✅ 8. Dry Run in Staging Environment

🗓 Target Deadline: Day 16–18

- Perform a full dry run of the entire migration

- Monitor logs, errors, time taken for each major step

- Perform random sampling for data validation

- Fix issues found during dry run

### ✅ 9. Final Migration Execution Plan

🗓 Target Deadline: Day 19–20

- Lock in official migration date/time

- Prepare rollback plan in case of failure

- Share final migration SOP with all involved teams

- Set up alerts and monitoring for post-migration validation

### 📎 Notes:

- A detailed migration checklist (Excel or Notion doc) should be maintained and signed off for each step.

- Maintain a migration issue log for tracking exceptions, delays, or manual corrections.

- Use pg_stat_activity, pg_locks, and pg_stat_user_tables for real-time monitoring during load.

# 1. Backup & Restore Strategy

• Take full logical backups of the source CDMS 2.0 database using pg_dump before any dry run or production migration.
• Store backups securely in versioned folders or external storage (e.g., S3, NAS).
• Prepare and test pg_restore scripts to verify rollback capabilities in staging.
• Document exact paths and backup file sizes.

# 2. Security & Access Control Planning

• Review and apply all GRANT statements, roles, and privileges in the target CDMS 3.0.
• Migrate function/view ownerships and validate role mappings.
• Disable unused roles and audit new permissions post-migration.

# 3. Post-Migration Validation Checklist

• Perform the following validations after data migration:
   - Row count comparison (source vs target)
   - Primary/Foreign key constraint violations
   - Null checks on NOT NULL columns
   - Data type and format consistency (e.g., timestamp)
   - Application-side functional validation
   - ENUM and lookup consistency checks

# 4. Tooling Documentation

• Declare all tools and utilities used:
   - ETL: psql, COPY, Python scripts
   - Monitoring: pg_stat_activity, pg_stat_user_tables, pg_locks
   - Logging: PostgreSQL logs, custom validation logs
• Document their versions and command syntax used during the migration.

# 5. Dry Run Acceptance Criteria

• Define criteria to validate a successful dry run:
   - 100% row count match for all key tables
   - No FK/PK or null constraint violations
   - All sequences reset and tested
   - Application login/session validation success
   - All logs reviewed with <1% error tolerance

# 6. Script Version Control

• Maintain all DDL, DML, and ETL scripts in Git or equivalent source control.
• Tag each version with timestamp and migration phase.
• Include change logs for schema modifications and value mappings.